SCOPE OF WORK

Yamaha Eid Offer AR Experience

Web AR Microsite | 3D Showroom | AR Bike View | Price Reveal | Lead Generation

| Project Name | Yamaha Eid Offer AR |
| --- | --- |
| Prepared For | Yamaha Bangladesh |
| Project Type | Web-based Augmented Reality Campaign Experience |
| Document Purpose | Scope definition for vendor briefing, production planning, and approval alignment |

1. Project Overview

Yamaha Bangladesh will develop a Web-based Augmented Reality microsite for the Yamaha Eid Offer campaign. The experience will be accessed through a QR code placed on digital advertisements and campaign creatives.

After scanning the QR code, users will enter a Web AR environment where a 3D Yamaha virtual showroom appears. The showroom will follow a section-based layout inspired by the locked reference image, with each area representing a Yamaha motorcycle category such as FZ Series, R Series, MT Series, and other agreed product categories.

Users will be able to explore bikes, view selected models in AR within their own environment, check product details, reveal the regular MRP and Eid offer price, and submit purchase interest through a lead-generation form.

2. Project Objectives

Create an engaging digital experience around Yamaha Eid Offers.

Allow users to explore Yamaha motorcycles through an interactive 3D showroom.

Enable users to view selected bikes in AR within their real environment.

Communicate bike details, MRP, and Eid offer prices in a premium format.

Generate qualified customer leads through a Book an Interest form.

Support digital PR, social media engagement, dealer communication, and sales funnel contribution.

3. Project Platform

The project will be developed as a Web AR microsite. Users should not need to download any mobile application. The experience should open directly through a browser after scanning the QR code.

Required Compatibility

Android smartphones

iPhones

Chrome browser

Safari browser

Mobile-first browsing experience

QR-based access from digital and offline touchpoints

4. User Journey

| Step | User Action | Experience Output |
| --- | --- | --- |
| 1 | User sees Yamaha Eid Offer digital advertisement | QR code is visible on the creative |
| 2 | User scans QR code | User is redirected to the Web AR microsite |
| 3 | Microsite loads | A 3D Yamaha virtual showroom appears |
| 4 | User explores showroom | Bike categories are visible in different sections |
| 5 | User selects a category | Bikes under that category are displayed |
| 6 | User clicks on a bike | Bike pops up in AR in the user’s real environment |
| 7 | User taps the bike | Bike details and interaction options appear |
| 8 | User clicks Price Reveal | MRP and Eid offer price are shown |
| 9 | User clicks Book an Interest | User is taken to a lead form |
| 10 | User submits information | Yamaha team receives customer lead data |

5. Detailed Scope of Work

5.1 Web AR Microsite Development

The vendor will develop a fully functional Web AR microsite for the Yamaha Eid Offer campaign. The microsite should be lightweight, responsive, visually premium, and easy to use for a general audience.

QR code-based entry

Mobile-first landing experience

3D virtual showroom environment

Category-based bike navigation

AR bike placement in user environment

Bike detail interface

Price reveal interaction

Lead-generation form

Thank-you/confirmation screen

Analytics and lead tracking support

5.2 3D Virtual Yamaha Showroom

The vendor will create a 3D virtual showroom inspired by the attached reference layout. The showroom should look like a premium miniature Yamaha display environment with multiple dedicated sections for different bike categories.

FZ Series

R Series

MT Series

Scooter category, if required

Additional Yamaha categories as agreed

Locked 3D Showroom Design Reference The attached reference image is locked as the primary showroom structure direction. It should guide the miniature layout, section-based zoning, top-view exploration, and category-style navigation. Medical/lab elements from the reference must not be copied; they must be replaced with Yamaha motorcycle showroom sections, Yamaha blue accents, and premium automotive styling.

Reference-Based Design Requirements

Miniature, section-based 3D environment style

Category-wise room or zone division

Premium Yamaha-inspired visual treatment

Clear product placement zones

Smooth mobile-first navigation

Modern lighting and material treatment

High-quality but optimized 3D assets

No unrelated elements such as microscope, lab rooms, ambulance, or medical icons

5.3 Bike Category Navigation

The showroom will include different bike category sections. Each section should allow users to select and explore bikes from that category.

| Category | Possible Bike Models |
| --- | --- |
| FZ Series | FZS FI, FZS V4, FZ-X, FZ 25 |
| R Series | R15 V4, R15M |
| MT Series | MT-15 |
| Scooter Series | RayZR, Fascino, if applicable |

The final model list will be provided by Yamaha before production.

5.4 3D Bike Model Development / Optimization

The vendor will create, convert, or optimize 3D bike models for the agreed Yamaha motorcycles. Each bike model must be accurate and aligned with official Yamaha product references.

Bike body shape, color, decals, Yamaha logo, model logo, and overall proportions must be accurate.

Headlight design, fuel tank shape, wheel design, exhaust, seat, handlebar, and side panels must be preserved.

No creative alteration should be made to the bikes without Yamaha’s written approval.

Models must be optimized for smooth mobile performance without visible quality loss.

5.5 AR Bike Placement

Once a user selects a bike, the bike should appear in the user’s real environment through AR.

Bike placement on floor/surface

Realistic scale and proportion

Rotation or angle adjustment

Smooth viewing from different angles

Tap-based interaction

Clear CTA for bike details and price reveal

5.6 Bike Detail Interaction

After the user clicks on a bike, the system should show key bike information. Product copy and technical details will be provided or approved by Yamaha.

Model name

Engine capacity

Key features

Color options

Regular MRP

Eid offer price

Campaign CTA

5.7 Price Reveal Feature

The AR experience must include a dedicated Price Reveal interaction. The reveal should feel exciting but clean, premium, and campaign-appropriate.

User clicks on the bike.

Bike detail panel appears.

User clicks the Price Reveal button.

Regular MRP is shown.

New Eid offer price is revealed with a premium animation.

Book an Interest button becomes visible.

5.8 Lead Generation Form

After clicking Book an Interest, the user will be redirected outside the AR view to a form where they can submit their information.

Full name

Mobile number

District/city

Preferred Yamaha model

Preferred showroom/dealer, if required

Purchase timeline, if required

Consent checkbox for future communication

After submission, users should see a confirmation message: “Thank you for your interest. Yamaha team will contact you soon.”

5.9 Lead Data Management

The vendor must ensure that all submitted lead data is properly collected and accessible to Yamaha. All customer lead data will be owned by Yamaha. The vendor cannot reuse, sell, or share this data with any third party.

Admin dashboard

Google Sheet integration

CSV export

Email notification

CRM integration, if agreed separately

5.10 QR Code Development

The vendor will generate a QR code that redirects users to the Web AR microsite. If required, multiple QR codes may be created for different campaign channels to track performance separately.

Facebook creatives

Instagram creatives

TikTok content

YouTube description or community posts

Dealer posters

Event materials

Digital PR materials

Website banners

5.11 UI/UX Design

The AR microsite and interaction screens should follow Yamaha’s premium brand identity. The user should be able to understand the experience without complex instruction.

Mobile-first design

Clean navigation

Yamaha brand color usage

Premium typography

Clear CTA buttons

Easy category selection

Smooth product browsing

Simple price reveal flow

Simple lead submission flow

Minimal clutter

Fast loading experience

5.12 Analytics and Tracking

The vendor should include basic analytics tracking to measure campaign performance and identify which bikes/categories generate the highest interest.

QR scan/landing page visits

Unique users

Showroom load completion

Category clicks

Bike model clicks

AR bike view interactions

Price reveal clicks

Book Interest clicks

Form submissions

Drop-off points

6. Testing and Quality Assurance

The vendor will conduct full testing before final deployment. Yamaha will provide final approval after reviewing the complete user journey.

QR code functionality

Microsite loading

Android device testing

iPhone testing

Chrome browser testing

Safari browser testing

AR placement testing

Bike scale testing

Category navigation testing

Bike detail accuracy checking

Price reveal testing

Lead form testing

Data export testing

Performance and loading speed testing

7. Hosting and Deployment

The vendor will be responsible for deploying the final Web AR microsite. The hosting duration, domain/subdomain responsibility, server support, security requirements, and maintenance period must be finalized before project confirmation.

Hosting setup

Domain/subdomain setup, if required

SSL/security setup

Live deployment

Server maintenance during campaign period

Bug fixing during support period

Final handover documentation

8. Key Deliverables

| Deliverable | Description |
| --- | --- |
| Web AR microsite | Complete browser-based AR experience |
| 3D virtual showroom | Category-based Yamaha showroom environment |
| Bike category sections | FZ Series, R Series, MT Series, and agreed categories |
| 3D bike models | Optimized models of selected Yamaha bikes |
| AR bike experience | Bike pop-up in user’s real environment |
| Bike detail panel | Model details, features, and color/options |
| Price reveal feature | MRP and Eid offer price reveal interaction |
| Lead form | Customer interest submission form |
| QR code | Campaign QR code for digital and offline use |
| Analytics setup | User journey and lead tracking |
| Testing report | Device, browser, and functionality testing summary |
| Final deployment | Live campaign-ready microsite |
| Handover files | Documentation, access, and lead management process |

9. Responsibilities

9.1 Yamaha Responsibilities

Final list of bike models

Official bike images and references

Bike specifications

MRP and Eid offer prices

Yamaha logo and brand guidelines

Campaign key visual, if available

Content/copy approval

Dealer/showroom information, if required

Feedback and approval at each stage

Access to analytics or CRM tools, if needed

9.2 Vendor Responsibilities

Requirement analysis

Technical planning

UI/UX design

3D showroom creation

3D bike modeling/optimization

Web AR development

QR code generation

Price reveal interaction

Lead form development

Analytics integration

Testing and bug fixing

Hosting and deployment

Maintenance support during campaign period

Final project handover

10. Approval Stages

| Stage | Approval Requirement |
| --- | --- |
| Stage 1 | Project flow and wireframe approval |
| Stage 2 | UI/UX design approval |
| Stage 3 | 3D showroom design approval |
| Stage 4 | 3D bike model accuracy approval |
| Stage 5 | AR prototype approval |
| Stage 6 | Price reveal and form flow approval |
| Stage 7 | Final testing approval |
| Stage 8 | Live deployment approval |

No final deployment should happen without Yamaha’s written approval.

11. Suggested Project Timeline

| Phase | Task | Estimated Duration |
| --- | --- | --- |
| Phase 1 | Requirement finalization and flow confirmation | 2–3 working days |
| Phase 2 | Wireframe and UI/UX design | 5–7 working days |
| Phase 3 | 3D showroom development | 7–10 working days |
| Phase 4 | 3D bike model preparation | 10–15 working days |
| Phase 5 | Web AR development | 15–20 working days |
| Phase 6 | Lead form and analytics integration | 3–5 working days |
| Phase 7 | Testing and revisions | 5–7 working days |
| Phase 8 | Final deployment | 2–3 working days |

Estimated Duration Total estimated timeline: 35–50 working days, depending on the number of bike models and complexity of 3D assets.

12. Out of Scope

The following items will not be included unless agreed separately:

Mobile app development

Paid media boosting

Social media creative design

Video production

Voiceover production

Advanced CRM integration

Dealer-wise automated lead distribution

Additional bike models beyond the agreed list

Major design change after approval

New campaign module after development starts

Offline event booth setup

Physical QR standee production

Long-term hosting beyond agreed campaign duration

Post-campaign maintenance beyond agreed support period

13. Quality and Performance Requirements

The final experience must meet the following standards:

Fast loading on mobile devices

Smooth AR placement

Premium showroom look and feel

Accurate Yamaha bike representation

Clear product information

Functional price reveal button

Functional lead form

Clean data capture

No broken links

No distorted bike models

No incorrect Yamaha branding

No low-quality rendering

No unnecessary visual clutter

14. Final Project Summary

The Yamaha Eid Offer AR project will allow users to scan a QR code from campaign advertisements and enter a Web AR microsite featuring a 3D Yamaha showroom. Users can browse bike categories, select a Yamaha motorcycle, view the bike in AR within their real environment, explore product details, reveal the Eid offer price, and submit purchase interest through a lead form.

The final output should be a premium, interactive, mobile-first AR experience that supports both brand engagement and lead generation for Yamaha Bangladesh during the Eid Offer campaign.

Strategic Recommendation Position this not as an AR gimmick, but as a digital-first Yamaha showroom experience that turns offer communication into measurable customer leads.